## Slide 1
Quality Control & Monitoring
Training for Medical education via innovative eTechnology
MediTec
Assistant Professor
Dr. Nazar S. Haddad
University of Basrah
College of Medicine

## Slide 2: Assumptions And Risks
Assumptions: Quality measures will be built into all WPs. Impact of all outputs will be assessed  Experience of coordinator and local coordinators on management and control of the project activity  Qualification of academic partners in quality control and recommendations  Skills of the project partners in JO and IQ on preparing relevant reports

## Slide 3: Assumptions And Risks
Risks:  Quality plan strategy and tools are not used effectively: Mitigated by training, construction and coordination  Knowledge and skills of partners in monitoring project activities  Insufficient quality of the local project control and monitoring in partner universities-
Which will be prevented by continuous distant monitoring of project steps by the local and overall project the coordinators.

## Slide 4
Quality control and monitoring mechanisms in place at all participating institutions.
Each participating institution, including EU partners, will have to prepare a short document highlighting in a schematic way which are the main Quality Control and monitoring

## Slide 5
Quality control and monitoring is provided by HTWK as coordinator.
HTWK has the overall responsibility to follow activities,
to access their implementation and
to secure that the achievement envisaged by the consortium and planned in the proposal will be reached.
All local coordinators of the project partners must send regular reports and presentations of project progress (e.g., courses methodology presentation) to HTWK.

## Slide 6
Some important parts of the project (like evaluation of courses and training materials, functionality of training center) will be checked during visits of specialists from EU partners to universities from JO,IR and IQ

## Slide 7
All the project progress will be shown at the project website
The project budget and costs effectiveness will be thoroughly checked using the strategy for the project.

## Slide 8: Quantitative Measure of Project Progress
The project progress will be measured quantitatively using following statistics:  Number of courses available for training courses on innovative Medical technology  Number of trained teachers, doctors and students in partners universities  Methodology, specifications publication  Access of participants to the equipment in the centers  Respect of deadlines and milestones quality of the deliverables  Project management and working procedure efficiency  Project meetings efficiency

## Slide 9
If the quality differs from the expected, the partners are granted for limited time intervals to improve it and correct mistakes. In such cases, the project coordinator and local project coordinators in are the responsible actors.

## Slide 10: Tasks
4.1 Quality control, monitoring and budgetary control 4.2 Monitoring of the development process 4.3 Expertise and quality control of developed methodical training and manuals 4.4 Project task supervision, result evaluation

## Slide 11
Estimated Start Date (15.10.2017) | Estimated End Date (15.10.2020)
Lead Organisation | EU partners and local coordinators
Participating Organisation | All partners

## Slide 12
Title | Quality control, monitoring and budgetary control | 4.1
Type | ☒ Event ☒ Report | 
Description | Local coordinators and admin. staff in HTWK and in JO,IR and Iraq carry out all quality control, monitoring, control budget and costs effectivity. Development of a quality plan and QA documents to evaluate the project. EU-partners check also the established center for training on innovative medical technology creation & work in JO,IR and IQ due to availability /stability/info exchange/course and training materials during visits and internet sessions. | 

## Slide 13
Due date | 15-09-2018
Target groups | ☒ Teaching staff ☐ Students ☐ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☐ Other

## Slide 14
Title | Monitoring of the development process | 4.2
Type | ☒ Event ☒ Report | 
Description | Monitoring of timely and qualitative matters of the implemented work by project partners is done by contractor and local coordinators. Teachers and specialists from EU partners evaluate training courses and training materials in JO,IR and IQ. | 
Due date | After each training and 10.10.2020 | 
Target groups | ☒ Teaching staff ☐ Students ☐ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☒ Other | 

## Slide 15
Title 4.3 | Expertise and quality control of developed training programs and manuals | 
Type | ☐ Teaching material ☐ Learning material ☒ Training material | ☒ Event ☒ Report ☒ Service/Product
Description | Quality assurance of the developed outcomes and outputs would be conducted by the competent partners. All partners, especially partners who are experienced from EU and partners countries would be ensuring the relevance of the developed courses and components to the current situation in partner universities. Expertise from EU partners would be responsible for ensuring the quality of the training materials and the application in training process. | 

## Slide 16
Due date | During the project life time and 15.09.2020
Languages | Arabic, English, Persian
Target groups | ☒ Teaching staff ☐ Students ☒ Trainees ☒ Administrative staff ☐ Technical staff ☐ Librarians ☐ Other
Dissemination level | ☐ Department / Faculty ☐ Institution ☒ Local ☐ Regional ☒ National ☐ International

## Slide 17
Title 4.4 | Project task supervision, result evaluation and reports | 
Type | ☒ Event ☒ Report ☐ Service/Product | 
Description | During all the project phases the project partners control the following:  The project phases are strictly directed to project work-plan  The input at the different project phases accords with the planned activities  The output/outcomes are in line with the aimed outcomes  Number of trained teachers, doctors and students in partners universities  Respect of deadlines and milestones quality of the deliverables These actions will be done through:  The project evaluation by the involved academic staff  The project evaluation by the involved the EU specialists  The project evaluation by the members of the steering committee  The training evaluation by students and trainers | 
Due date | During the project life time and 10.10.2020 | 
Target groups | ☒ Teaching staff ☒ Students ☒ Trainees ☒ Administrative staff | 

## Slide 18: Thank you