## Slide 1
Training for Medical education via innovative eTechnology
MediTec
WP6
Management
23.02.2018
Dr. Riyadh Qashi

## Slide 2
How to manage the project MediTec successfully?
i. Remarks – experiences, needs, …
ii. Tasks of the WP
iii. Steering committee
iv. Problem: last payment (10% of means)
v. Staff costs
vi. Travel costs, costs of stay

## Slide 3
i. Remarks – experiences, needs, …
There are several limitations due to:
rules of EACEA in Brussels, guidelines
rules of JO/IQ/IR financial systems,
rules of DE/CZ/SK/MA financial systems
DE (DE rules, Saxony rules and
HTWK rules : Central administration in HTWK ,Rectorate of HTWK, §§§)
Monitoring visits, reporting, auditing (Consequences, performance of audits, proof of payments, co-financing,….. )
Changes in project implementation

## Slide 4
ii. 3 Tasks of the WP Management
means:
overall responsibility for success of entire project
financial and other reports regularly sent from local coordinators to grant holder
budgetary control
responsibility of partners for implementation and project support by local authorities
adequate and fair participation of all partners
Coordination of meetings
Management of project activities

## Slide 5
6.1 Coordination of meetings
- for ensuring
  efficient implementation and quality,
  inclusion of all consortium members
  communication between partners.
HTWK performs overall project management and coordination, But only together with the local coordinator and WP leaders and off course all partners
LC and WPL are responsible for local management and organization of activities

## Slide 6
6.2 Controlling of the project activity, Monitoring and evaluation of results
All partners will work together on:
Control of project activities
Contol by LC and WPL:
monthly/weekly control of project quality and
results summarized and documented
activities evaluated and
Results and reports after each activity must be sent to the HTWK

## Slide 7
6.3 Reporting and control of the budget
budget calculation & control, all local coordinators are responsible
by LC + WPL + responsible person for financial report, controlled by project coordinator
financial documentations required for transparency in original
use of financial means before starting + after performing activities,
financial reports after each activity (invoices and calculations must be sent in original)

## Slide 8
iii. Steering, quality and technical committee
Steering committee for activities’ coordination
SC is responsible for many issues, for example:
strategic decisions for project performance & implementation;
management of project activities;
internal quality control, assessment, monitoring and reporting;
conversion project applications to a practical plan.
conflict management;
budgeting;
evaluation of the project results

## Slide 9
iv. Problem: last payment (10% of means)
only after successful Final Report
may be reduced
but: delivering all invoices

## Slide 10
Partnership Agreement
Budget
Staff Reprots
Travel Reports
Next week